## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
6 The Lawns
Ladgate Lane
Middlesbrough
TS4 3SA
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 20-5866
DATE OF REPORT: 10/02/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 6 The Lawns
Ladgate Lane
Middlesbrough
TS4 3SA
Carried Out On | 14/01/2021 24/12/2020 22/12/2020, 13/01/2021
Survey Completed By | Phillip Rogerson
SECTION 2: Introduction
14/1/21 Mrs Evis has leak through utility ceiling LG23-12-20 I have had the emailedabout a leak through the kitchen ceiling, he said that he pointed it out to Zenith Engineer but was told someone else would need to attend? Advised leak patchon ceiling in kitchen. Wood where boiler is located is all swelled and needs replacing as still leaking

## Report
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
SECTION 3: Report
Small stain on kitchen ceiling, checked all visible pipework around cylinder and bathroom, no visible leak, possible leak under floor or bath/shower screen, further investigation required. 10.05am till 10.40 am Attended site on 14-1-21. Water dripping from utility room door frame and water stain on utility room ceiling. Checked cylinder cupboard and under bath and both seemed dry. Cut hole in utility room ceiling to find a leak coming from plastic elbow on cold feed going to bath. Also found second leak on plastic connector which was concealed in expanding foam under bath. Both leaks repaired and tested ok. Photos emailed to admin, Dave Hunter and Josh. Onsite 2 hours 30 mins. PR

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 20-5866
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes