## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
25 The Elms
Chester-Le-Street
County Durham
DH2 3EJ
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-6151
DATE OF REPORT: 14/06/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 25 The Elms
Chester-Le-Street
County Durham
DH2 3EJ
Carried Out On | 18/01/2021, 16/01/2021, , 14/06/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Job Description - Overheating issues within the flat, the tenant is struggling with the heat.

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
SECTION 3: Report
Attended site to find flat excessively hot due to no control over heating system. I re attached the UFH actuators to the heating circuits and checked each thermostat independently to make sure it operated the pump. actuator heads will be replaced as a precaution with them previously getting wet due to a leak to limit the chance of one of them failing in the near future. The mixing valve was also turned down whilst on site to limit excessive heat getting into the flat over the weekend, this will need to be set to the desired temperature during works to replace actuator heads. 2 hours out of hours not chargeable ? Onsite 1245 18/01/21 Attend site check 4 x rooms stats and 4 x actuators room stats all ok but had to replace bedroom 1 and living room actuator which site supplied as not working correctly (shutting off). Test all ok find tmv not working correctly and putting 58° heating water to underfloor manifold set this as low as I could and order new Offsite 1400 fow new tmv needed Attend site 0800 14/06/21 wait for tennant to get up but turned away at 0915 as she's not feeling well to return to site after dinner, Attend site 1600 isolate HIU unit and drain down , strip out the mixing valve and brass nipples and replace with new mixing valve and nipples, resemble and testvall ok check for leaks and commission and test all ok. Heating temp set at 55° all ok and working Offsite 17.30 complete Parts used 1 no calfide mixing valve 3 no 34"brass nipples

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
SECTION 4: Photos
Room / Area
Description
Notes
Old tmv stripped out
Room / Area
Description
Notes
New tmv installed and commissioned
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6151
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes