## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
4 Finley Road
Fixton
York
YO11 3UF
CARRIED OUT ON BEHALF OF
HG Morgan Sindall
REPORT NUMBER: 21-6355
DATE OF REPORT: 04/02/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | HG Morgan Sindall
Address | Sheffield South
Yorkshire
S9 2UB
Site Address | 4 Finley Road
Fixton
York
YO11 3UF
Carried Out On | 26/01/2021
Survey Completed By | Darren Reay
SECTION 2: Introduction
Inspection Visit Checklist - Air Source

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
SECTION 3: Report
Systems installed: o Ground Source Heat Pump o Air Source Heat Pump. X o Oil Boiler o Gas Boiler o LPG Boiler o Solar Thermal o Domestic Hot Water. X o Sealed System. X o Open System Make and Model of Heat Pump: Daikin; ERSQ011AAV1 Heat Pump Serial Number:--------------6910122------------------------- DHW Cylinder Serial Number:------------000154BN--------------------------- Heat Pump Controller Heating Return Set Point:----------------------60------------------------------ Immersion fitted:----------------------------Yes----------------------------- Bivalent Point:------------------------------------------------------------------------ Cylinder Target Temp:----------------------42------------------------------------ Compressor Run Hours:----------------------NA------------------------------- DHW Immersion Run Hours:--------------NA------------------------------- Heating Curve Set Point:------------------------weather comp-------------- Heat Pump Control method: o Weather Compensated X o Fixed return o BMS o Other Heating Temp Flow:----------------------------55--------------------------------- Heating Temp Rtn:------------------------------34-------------------------------- Heating Dt:----------------------------------------21-------------------------------- DHW Temp Flow:---------------------------------45------------------------------- DHW Temp Rtn:----------------------------------38-------------------------------- DHW Dt:--------------------------------------------7--------------------------------- Check refrigerant in Sight Glass:--NA------------------------------------------ Check Load Side for Air:----------------------ok--------------------------------- Comments - Found water strainer missing. System now has no protection from debris entering the heat pump heat exchanger Air Source Heat Pump o Clean air ducts, grilles, condensate tray etc:--------NA--------------- o Wash evaporator:-----------------------------------------NA-------------- o Check pump direction/rotation:------------------------Y---------------- o Check and clean strainer:--------------------------------Y----------------- o Check flow rate:--------------------------------------------Ok--------------- o Test aerators:-----------------------------------------------Y---------------- o Check joints for leaks:-----------------------------------Y----------------- o Glycol refractometer reading:--------------------- -20------------- o Check insulation:-----------------------------------------Ok----------------- o Expansion vessel information:----------------------charge fine-------- Solar Thermal o Type of system:--------------------------------------------------------------- o System Pressure:-------------------------------------------------------------- o Check pipework for leaks:-------------------------------------------------- o Check content of discharge vessel:--------------------------------------- o Check roof penetrations for leaks:--------------------------------------- o Check pipe insulation:------------------------------------------------------- o Check collector fixations:--------------------------------------------------- o Check pump function:------------------------------------------------------- o Check sensor readings:------------------------------------------------------ o Check electrical connections:---------------------------------------------- o Check expansion vessel:---------------------------------------------------- o Check pH of Glycol:----------------------------------------------------------- o Check refractometer reading of glycol:--------------------------------- o Appearance of glycol:-------------------------------------------------------- o System safe to use:----------------------------------------------------------- Comments - NA Domestic Hot Water o Drain Cylinder and remove PRV cartridge:---------------------- o Check combination valve:------------------------------------------- o Check expansion vessel:------------y-------------------------------- o Refill cylinder:---------------------------------------------------------- o Remove air from cylinder:-------------------y---------------------- o Check expansion release valve:---------------y------------------- o Check T&P valve:-------------------------------y--------------------- o Test three port operation:---------------------y-------------------- o Test two port operation:-------------------------------------------- o Test Circulation pump:-------------------------y-------------------- o Check immersion:--------------------------------y-------------------- o Check setting on immersion dial:-------------60----------------- o Check high limit stat:--------------------------y---------------------- o High limit stat temp setting:--------------------70----------------- o Check header tank F&E:--------------------------------------------- o Check cold water cistern:-------------------------------------------- o Check pipe work configuration:----------------ok---------------- Comments - NA Heating System o Heating Circuit pressure:2 bar operating/hot o Inspect heating pump:y o Check rotation and direction:good o Clean strainers: strainer cartridge missing o Expansion vessel information:ok o Inspect UFH manifold: o Inspect radiators:y o Test TRVs:pin ok o Inspect electrical installation: o Test heating controls:ok Additional work required/recommendations - New y strainer cartridge needed for strainer, fine mesh cylindrical filter

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6355
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes