## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
St Johns Court
Front Street
Sacriston
DH7 6JA
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-6668
DATE OF REPORT: 15/03/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | St Johns Court
Front Street
Sacriston
DH7 6JA
Carried Out On | 25/02/2021, 03/03/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Commercial engineer to visit St Johns this afternoon in an attempt to identify and repair these legacy issues.

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
SECTION 3: Report
LPC 25.2.21 1535 - 1630 Gained access to flat 10 found that Tennent having ongoing issues with DHW , immersion heater keeps overheating and reqs stat resetting . Reccommed fitting new immersion to elson tank , drain down and inspect . Spoke to Jim from Karbon and confirmed that I am going to order 5 x new immersion heaters and spares, to be kept on site . Information sent over to Spencer at border heating, to order items as req. Same for flats 7 , 10 and 16 . Pick up parts from wholesalers and travel to site onsite 0830 Gain access to flat 10 and isolate electrical supply to the thermal store water heater, and drain down find drain off blocked clear as best as I can once drained replace the element and drain off, fill and vent. Cannot test the operation electrical supply as timer not on till 1300 and there is no way to over ride will contact tenant later to day to make sure all working. 9 other emersion elements left in the boiler room. Complete 1230 Parts used 1 no Elson emersion element 9 left in plant room for spares

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6668
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes