## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
23 Matfen Court
Chester-Le-Street
County Durham
DH2 2TX
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-6999
DATE OF REPORT: 31/03/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 23 Matfen Court
Chester-Le-Street
County Durham
DH2 2TX
Carried Out On | 17/03/2021, 31/03/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Leak into 23 believed to be coming from communal heating - See email for further info

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
SECTION 3: Report
Attend site 1700 for a leak Find water coming from bathroom light check flat above in bathroom find nothing leaking need to get the ceiling down in flat 23 bathroom to see where the water is coming from, ceiling needs an asbestos check as there are asbestos stickers in risers and I other areas. This will have to be carried out by an approved contractor. I suspect that it could be the shower in flat 32 directly above but the bathroom is a wet room and no access to shower tray Offsite 1830 fow Attend site 0800 31/03/21 Attend site with Adam to trace the leak in the ceiling in flat 23 , check asbestos report and start to take ceiling down but find this ceiling is over boarding an artexed ceiling so stop work and request another asbestos check on this, gain access to flat 32 (above) to see if there's a leak from above, contact Andy Sutherland from Karbon and he instructed us to take tiles off on the boxing in to see if the wet room floor is leaking, once stripped off we found the floor to be soaking, the wet room floor needs to be lifted now to allow access. Andy Sutherland has taken the lead on this now as the tennant in flat 32 has health issues which require her to have access to the toilet and the shower at all times and thr gentleman in flat 23 has no shower and water leaking in to his bathroom through the ceiling light and possibly asbestos on the ceiling which is now uncovered Offsite 11.30 fow

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-6999
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes