## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
Athlone Court
Blyth
Northumberland
NE24 1EW
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-7006
DATE OF REPORT: 07/07/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | Athlone Court
Blyth
Northumberland
NE24 1EW
Carried Out On | 18/03/2021, 24/03/2021, 29/03/2021, 08/04/2021, 12/04/2021, 05/05/2021, 06/05/2021, 01/05/2021, 10/05/2021, 11/05/2021, 12/05/2021, 13/05/2021, 07/07/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Plant refurbishment as instructed by Karbon Homes: Jewson - 0250/00112641 -298.28 Graham - 0401/00791339 - 26.26

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
SECTION 3: Report
Onsite 0745 Offsite 2000 12/03/21 onsite 0745 offsite 1500 04/05/21 0800 survey hot water alterations, check in loft tracing pipework to tank. Offsite 1145 05/05/21 onsite 0800 convert dhw system from tank fed to unvented. Install one of the new dhw caloifers Offsite 1730 06/05/21 onsite 0800 offsite 1400 10/05/21 onsite 0800 Isolate and drain down the dhw circuit and cut out out the pipework with the old dhw pump installed and repipe and install new pump into the return circuit fill and vent , check that the tennants have hot water to there flats. Offsite 1230 11/05/21 1030 onsite install pipework and fixings secure flues at height make a list to finish off install and to cut out out the old pipework. Offsite 1600 Attend site 12/05/21 0800 install boiler room offsite 1630 Onsite 0800 13/05/21 pipework now complete , instructed Tyne Tees thermal to lag pipework and bms controls to be installed offsite 1200 Attend site 07/07/21 0830 Attend install unistrut to allow the flues to be secured Hard wire pumps primary and heating to switch fused spurs Strip out old flues and repair roof to make water tight Offsite 1600

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
SECTION 4: Photos
Room / Area
Description
Notes
Pumps all wired in
Room / Area
Description
Notes
Unistrut installed so flues can be secured
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7006
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes