## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
45 Cookson Place
Stanley
County Durham
DH9 6YT
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-7009
DATE OF REPORT: 19/04/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 45 Cookson Place
Stanley
County Durham
DH9 6YT
Carried Out On | 18/03/2021, 29/03/2021, 30/03/2021, 12/04/2021, 14/04/2021, 19/04/2021, 20/04/2021
Survey Completed By | Adam McCallum
SECTION 2: Introduction
Heating system conversion

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
SECTION 3: Report
Current appliance is a vaillant ecotec plus system boiler located in ground floor kitchen with horizontal flue to outside. Gas supply pipework is in 15mm copper, in the current position there is access to heating primary pipework, hot and cold water pipework and existing condensate pipework. In the first floor bedroom is an airing cupboard consisting of y plan system pipework and Indirect hot water cylinder with feed and expansion tanks in the loft space. Advice that due to clearances for flue in the kitchen a vertical flue be installed with 1 meter extension. Images provided via separate email 29/03/21, system flushed with magna cleanse ready for system conversion following day, another cleaner added to system and left on over night to be flushed out by installer. Boiler and flue left on job for following day. Advise needs 4 x 15mm TRV's for kitchen lounge and bedroom. GW. 19/04/21 New boxing made to surround new boiler bottom top and side to cover old boiler vent. Ceiling repaired and inspection hatch fitted so maintenance can be done on flu.

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7009
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes