## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
Carisbrooke Court
Sunderland
SR1 3SN
CARRIED OUT ON BEHALF OF
Castles & Coasts Housing Association
REPORT NUMBER: 21-7438
DATE OF REPORT: 20/04/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Castles & Coasts Housing Association
Address | Arcadia House
Balliol Business Park
Newcastle Upon Tyne
NE12 8EW
Site Address | Carisbrooke Court
Sunderland
SR1 3SN
Carried Out On | 14/04/2021, 20/04/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Replace Flue - Nation Wide Chimneys

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
SECTION 3: Report
Arrange new flue install 0930 1100 Reattended site 1545 to test hot water boilers to allow them to be switched back on after being switched off due to flue issues Turned both boilers and wait 20 mins then carry out a co2/co sweep of the plant room. After 20 mins check readings 0 ppm co 899ppm co2 Visually inspect the flue and carry out a smoke test , no spillage so the boilers can be left on as there is no spillage from the flue and no products of combustion leaking into the plantroom . The flue is being replaced next week which will bring this up to current standard. These works need carried out ASAP Boilers being turned and left on. Attend site 20/04/21 to open up boiler room to allow access for ncc to install new flues , isolate boilers. Onsite 0800 offsite 0900 Attend site 1200 20/04/21 recommission boilers after new flues fitted. Flues now working and boilers up and running. Offsite 1300 complete

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
SECTION 4: Photos
Room / Area
Description
Notes
Room sweep readings after 20 with boilers both on
Room / Area
Description
Notes
Temporary repair
Room / Area
Description
Notes
Lee Chatterton has left this at risk notice
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7438
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes