## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
5 Carisbrooke Close
Washington
Tyne and Wear
NE37 2HZ
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-7575
DATE OF REPORT: 27/04/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 5 Carisbrooke Close
Washington
Tyne and Wear
NE37 2HZ
Carried Out On | 23/04/2021, 26/04/2021 27/04/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
FOW on works as required Adapt current system to indierect type fed from baxi boiler in the kitchen 28mm 3 port valve to be replaced and B port to be connected to existing indirect hot water tank. Hot water system is currently direct type.

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
SECTION 3: Report
Attend site isolate and drain down heating circuit to allow alterations to the pipework to allow installation of flow and return to the existing calorfier. Install new pipework and fill and vent system is open vent and had to be back filled to get it going , by 5 pm only some of the rads heating up so will require a visit tomorrow to check all ok Dhw boiler in laundry had to be decommissioned and pipework altered to allow new pipework to be run so only calorfier suppling hot water. DHW ALL UP AND RUNNING OK Offsite 1730 fow Attend site 0800 Check heating through out and find 2 no radiators not working pull through heating water by removing radiators and clear airlock, refit rads and test all ok , show Jim the electrician how I've temporarily wired up the DHW pump and how the new heating controls should be wired Offsite 1015 complete

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-7575
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes