## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
Holborn House
Commercial Road
South Sheilds
NE33 1EA
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-8025
DATE OF REPORT: 18/06/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | Holborn House
Commercial Road
South Sheilds
NE33 1EA
Carried Out On | 17/06/2021, 18/06/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Upgrade condensate, repair trap on boiler, paint and seal gas pipe and lag flow and return pipes

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
SECTION 3: Report
Attend 0800 till 0900 with ncc to let them in to replace the flues Flu3s fitted Reattend 1145 install condensate for the new flue , 5 new drain points all connected in to one using 11/4" waste and a close couple s trap. Extend all pipework from boiler blow offs to terminate at ground level x 3. Replace o rings on no 3 boiler condensate trap test for leaks all ok. Lagging on order will pick it up in morning to reatend and fit Offsite 1445 Attend site 0845 18/06/21 after picking lagging up Fit lagging to header pipework on boilers and paint another coat of gas id orca paint on gas main in plantroom Offsite 1000 complete

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
SECTION 4: Photos
Room / Area
Description
Notes
No condensate pipework
Room / Area
Description
Notes
Condensate pipework all tied in 1 1/2" waste pipe
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8025
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes