## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
The Victoria Centre
Unit 2
Trafalgar Street
DH8 5AP
CARRIED OUT ON BEHALF OF
Eagle Crest (Consett) Limited
REPORT NUMBER: 21-8947
DATE OF REPORT: 13/07/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Eagle Crest (Consett) Limited
Address | 3 Castle Gate
Castle Street
Hertford
Herts
SG14 1HD
Site Address | The Victoria Centre
Unit 2
Trafalgar Street
DH8 5AP
Carried Out On | 02/07/2021, 05/07/2021
Survey Completed By | Dave Aston
SECTION 2: Introduction
Installation of a new mains cold water supply fed from an adjoining unit, including an inline cold water meter for usage monitoring/billing accordingly.. The new pipework route will be fireproofed and boxed where required. The new/existing cold water pipework will be chemically flushed before occupancy/usage.

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
SECTION 3: Report
Attend site 0800 Install new water main fed from betting shop through to Yorkshire linen install isolation valves and a new water meter suppling Yorkshire linen clips all pipework as require 2 x holes to fire stop 1 in Yorkshire linen and 1 in betting shop to make fire compliant. Clear flow attended to chlorinated the new pipework. Need to return to site Monday to flush out chlorine Parts used 15mm speed fit pipe 15mm speed fit fittings 15mm water meter 15 mm isolation valves x2 Offsit 1330 fow Onsite 0830 05/07/21 Attend site with clear flow to carry out water tests Offsite 0900 complete

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-8947
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes