## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
8 High Shaw
Prudhoe
NE42 6LD
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 21-9346
DATE OF REPORT: 29/07/2021
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 8 High Shaw
Prudhoe
NE42 6LD
Carried Out On | 27/07/2021, , 29/07/2021
Survey Completed By | Carl Stephenson
SECTION 2: Introduction
Kitchen & Bathroom Install

## Report
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
SECTION 3: Report
27/07/21 Attended site 8am, started at No.22 high shaw as plasterers where in No.8 high shaw all day, Removed bath, toilet and hand basin from site,1st fixed kitchen, Fitted new bath, toilet and sink basin plumbed and tested new suite for leaks everything ok 29/07/21 Attended site 8am, started ripping old bathroom out, new bath needed spinning so additional pipe work required, sink and toilet also additional pipe work required, bathroom all completed and checked for leaks, just gas hob need connecting in kitchen.

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 21-9346
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes