## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
14 Priestclose Cottages
Prudhoe
Northumberland
NE42 5DL
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 22-22098
DATE OF REPORT: 07/09/2022
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | 14 Priestclose Cottages
Prudhoe
Northumberland
NE42 5DL
Carried Out On | 30/08/2022, 05/09/2022, 03/09/2022, 06/09/2022, 07/09/2022
Survey Completed By | Rhys Brown
SECTION 2: Introduction
Wet room installation - change all furniture as existing

## Report
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
SECTION 3: Report
PN 3/8/22 No work done as floor needs plying Electric shower not isolated from electric Back to wall toilet on job should be Pan and low level cistern Bathroom stripped out Tiler has tiled behind basin and WC WC installed and basin pipework capped off Shower tray fitted and wastes complete Basin fitted Bathroom still needs electric shower fitted once tiles dry Shower fitted

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 22-22098
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes