## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
Primrose Court
Hesleden Road
Blackhall
TS27 4NX
CARRIED OUT ON BEHALF OF
Believe Housing
REPORT NUMBER: 23-27397
DATE OF REPORT: 01/02/2023
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Believe Housing
Address | Coast House
Spectrum 4
Spectrum Business Park
Seaham
SR7 7TT
Site Address | Primrose Court
Hesleden Road
Blackhall
TS27 4NX
Carried Out On | 01/02/2023
Survey Completed By | Rhys Brown
SECTION 2: Introduction
Install / Renew Bath shower mixer and shower hose to Void Flat. Building code 1089, void keysafe 5612

## Report
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
SECTION 3: Report
When arriving on site today, I was greeted by the manager who showed me flat seven. When in the flat decided that we would not be able to fit a bath shower mixer to the wall. It was on originally due to there being a window. Instead we have opted to fit shower boards to the walls to protect them as they are just plasterboard, then fit a shower head on the wall to the right of the original position of taps. For the installation, the toilet and possibly bath may have to come out as the space is very tight with it being a shallow bath. Please see below the size of walls which will need to be boarded. Walls to board- 1580x 1830 690x1830 690x1330

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-27397
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes