## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
Pembroke Court
Hylton Lane
Downhill
SR5 4DF
CARRIED OUT ON BEHALF OF
Castles & Coasts Housing Association
REPORT NUMBER: 23-36948
DATE OF REPORT: 30/01/2024
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Castles & Coasts Housing Association
Address | Arcadia House
Balliol Business Park
Newcastle Upon Tyne
NE12 8EW
Site Address | Pembroke Court
Hylton Lane
Downhill
SR5 4DF
Carried Out On | 21/09/2023, 20/12/2023
Survey Completed By | Craig Towart
SECTION 2: Introduction
6 Monthly Mechanical checks on Plant located in Plantroom, Laundry Room & Bin Store.

## Report
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
SECTION 3: Report
Ct 20/12 2x remeha 210eco pro boilers 1=operational 2= operational 1x calorifier operational small leak on cold feed ( would need isolated drained down and re sealed with thread tape or locktite and paste and re fitted picture in with report) Leak on heat exchanger on calorifier also attached photo 1x Dhw expansion vessel set at 3.5 bar 1x ch expansion vessel set at 1.5 bar Lagging has sections missing Gauges and sensors operational Valves operational 1x pressuration unit operational 6x prv operational Shunt pumps 2x grundfos tpd 80-120/2 1= operational amps 2.5 2= operational amps 2.7 Vt pumps 1x wilo yonos maxo 50/0.5-12 operational amps 0.7 Dhw primary pump 1x grundfos ups 32-80 al 180 operational amps 0.5 Dhw circulation pump 1x grundfos up 20-45 n 150 operational amps 0.4 Dhw secondary return pump 1x Grundfoss data badge missing operational amps 0.3 1x vt valve Siemens acatix sql33 operational 1x 3port valve Siemens acvatix sq565 operational 1x interlock operational Water sample awaiting results I have also tided plant room as the lagging that has been removed off pipe work has just been stuffed in pieces behind calorifier all bagged up and removed from site.

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-36948
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes