## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
Vicarage Court
Studley Road
Hartlepool
TS25 1TN
CARRIED OUT ON BEHALF OF
Karbon Homes
REPORT NUMBER: 23-37206
DATE OF REPORT: 29/04/2024
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Karbon Homes
Address | Number Five
Gosforth Park Avenue
Gosforth Business Park
Newcastle upon Tyne
NE12 8EG
Site Address | Vicarage Court
Studley Road
Hartlepool
TS25 1TN
Carried Out On | 06/09/2023, 07/09/2023, 08/09/2023, 11/09/2023, 13/09/2023, , 15/09/2023, 03/01/2024
Survey Completed By | Graham Parker
SECTION 2: Introduction
Plant Room audit and remedials

## Report
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
SECTION 3: Report
Ct 6/9 Audit done sent to Dave. Ordered materials to complete jobs Ct 7/9 Started repairs completed dhw so they are up to standard both secondary return blow off and cut old pressure reducing valve out. Complete condensate so piped up with correct materials. Piped the pump differentionals in with out the million connex fittings. Ct 8/9 continued with list all that is left is dosing pot to move and alter pipes. And disconnect old pressuration unit but no manger on site to get permission to turn mains water off. Also had to replace extension lead as electric trip in plant room and had to find correct trip switch. Ct11/9 Unable to break into steel pipe where would be shortest run due to old steel pipe not budging and not wanting to risk damaging. Will have to pipe from exciting dosing pot all the way around. Old pressuration unit disconnected Ct12/9 Repiped dozing pot so it’s accesable and don’t need to climb over Poe work to get. Cut high limit stats in that had been missed out of plant room. And got rid of all big rubbish and gas water heater with Tony. Ct 15/9 Found leak on legianala pump on bottoms of cyclinder 1 drained down stripped out but on stripping out noticed the plastic body threads go into be cracked. So capped off both pipes with 22mm blanks as new pump required. Cut out 15mm pipe work feeding pressuration unit as looked bad and potential to cause leaks with all cones fittings. Cut in overflow pipe to pressuration unit nut off tun dish missing so will need to source a new one wolsley Hartlepool didn’t have anything to fit. Tidied boiler room and made sure all rubbish removed and swept up. FoW required fit new pump and nut Materials used 12x 22mm 90 xpress 6m 22mm copper 4x22mm compression gate valves 4x22/15 center T XPRESS 2x long stem drain offs 5x 22mm rubber clips 3x condensate 90 1x condensate t 4m condensate pipe 1x 2” connector 2x2”- 1 1/4 reducer 2x1 1/4 to condensate reducer 10m 8mm copper 4x 8mm connectors ( needed rings) 16x 28mm xpress 90 16x clip build ups. 15m 28 copper 4x 28 male ion 2x 15mm female ion 6x 15mm xpress 90 3m 15mm copper 1x 2 white solvent t 03/01/24 GP Carried out survey of what works is required to get job closed down

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-37206
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes