## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
29 Eshwood View
Ushaw Moor
Durham
DH7 7FD
CARRIED OUT ON BEHALF OF
DAMHA
REPORT NUMBER: 23-38913
DATE OF REPORT: 19/01/2024
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | DAMHA
Address | Durham Aged Mineworkers Homes
P.O. Box 31, The Grove
168 Front Street
Chester Le Street
DH3 3YH
Site Address | 29 Eshwood View
Ushaw Moor
Durham
DH7 7FD
Carried Out On | 18/01/2024, 19/01/2024
Survey Completed By | John Bolton
SECTION 2: Introduction
Planned install for LST rads

## Report
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
SECTION 3: Report
When I arrived the tennant advised he had called in with a no cold water supply fault into the office. Traced fault to frozen cold water supply to everywhere but the kitchen sink. Went to screwfix to collect an extension lead to put into the loft to defrost pipes ( plastic) with fan heater I had on the van. Returned and got the water flowing carried out commission on boiler to get get into the house and going to start fitting the radiators at 13:30 Went over radiator sizes with James and they were incorrect with the sizes he had. Called Wolsley Consett and they confirmed that they were the rad sizes of the radiator inside. Started to remove old radiator and was asked to go onto another Job. 19/01/24 Started at 8 removed and fitted new LST rads and tested working ok.

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 23-38913
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes