## Cover
ZENITH MECHANICAL SERVICES
Plumbing & Gas Services
82 Viewpoint Business Centre, Consett, County Durham, DH8 6BN
Contact Number: 01207 693 849
Email: admin@zenithmechanical.com
REPORT ON
78 Beaconsfield Street
Newcaste Upon Tyne
NE4 5JN
CARRIED OUT ON BEHALF OF
Homegroup N1/N2
REPORT NUMBER: 24-52407
DATE OF REPORT: 14/08/2024
Registered in England Company No. 923602
Directors: Josh Hodgson and David Hunter |  | Gas Safe registration number: 527432

## Contents
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
Contents of Report
Section 1 | Job information
Section 2 | Introduction
Section 3 | Report
Section 4 | Photographs
SECTION 1: Job Information
Client | Homegroup N1/N2
Address | One Strawberry Lane
Newcastle Upon Tyne
NE1 4BX
Site Address | 78 Beaconsfield Street
Newcaste Upon Tyne
NE4 5JN
Carried Out On | 14/08/2024
Survey Completed By | Paul Nichol
SECTION 2: Introduction
Carry out 1st fix on kitchen and test gas and cap off - Radiator needs moved and replaced and also gas pipe needs moved as part of the first fix

## Report
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
SECTION 3: Report
PN 14/8/24 First fix sink complete Waiting for boards under floor boards to be tested for asbestos Radiator to pick up from wolsely Scotswood road on 15/8/24 Already been ordered Reference/ beaconsfield 1st fix complete – 2nd fix complete – Any other works complete – Any Gas works completed – Soundness/Tightness test gas supply – If gas pipe altered or installed complete CP12 including full regulation 26.9 checks. (Operating Pressure, Heat Input, Flue Gas Analysis or flue checks) If no Gas pipe altered Complete a gas certificate showing all gas appliances with visual checks only and add comments as work completed testing gas supply only – Take a picture of gas soundness test at 20mb and submit image – Add/submit any additional notes or images you deem necessary such as existing damages, issues, or concerns – Submitted Images of before during and completed works, such as before a 1 st fix, the actual first fix then 2 nd fix or completed works. Any Follow-on Works required – Give as much information as possible.

## Photos
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes
ZENITH MECHANICAL SERVICES
Report Number | 24-52407
SECTION 4: Photos
Room / Area
Description
Notes
Room / Area
Description
Notes
Room / Area
Description
Notes